## Phase Estimation
Phase | Task ID | Task | Description | Assign to | Est. Days | Buffer 20% | Total Days | Est. Weeks | Cost | Comments
Phase 0 — Design & Setup
| 0.1 | UI/UX Wireframes | Wireframes for all 6 views (Finder, Roster, Pipeline, Deals, Patterns, Admin), creator detail, proposal flow, dashboard mockups, approval workflow UI, mobile responsive, client sign-off | Mansour | 8 | 1.6 | 9.6 | 1.92
| 0.2 | Process Flow Diagrams | Proposal lifecycle, AI recommendation flow, approval workflow, rate card calculation, social data refresh, creator onboarding, media kit extraction | Ghassan | 2 | 0.4 | 2.4 | 0.48
| 0.3 | VPortal API preperation | Document cross-schema dependencies (Supplier, Client, BU, Project, ProjectLine, Item), confirm Identity/JWT sharing, confirm SignalR, document needed API calls | Ghassan | 0.2 | 0.04 | 0.24 | 0.048 |  | GS: already working on it for AI integration
| 0.4 | Solution Structure Setup | Backend module structure, React app scaffold (Vite/MUI6), wire auth, Azure Blob containers, CI/CD pipeline | Barzan | 1 | 0.2 | 1.2 | 0.24
| 0.5 | Sentry Monitoring | Error tracking for API and AI failures, alert routing, performance monitoring | Barzan | 0.5 | 0.1 | 0.6 | 0.12
|  | Phase 0 Subtotal |  |  | 11.7 | 2.34 | 14.04 | 2.808 | 1965.6
Phase 1 — Core VCI Platform (without AI)
1.1 |  | Creator Feature |  |  | 5.6 | 1.12 | 6.72 | 1.344
1.1 | 1.1a | Creator Entity Layer | CreatorSocialMetrics, CreatorRateCard, CreatorTravelCosts, CreatorBrandConflict, CreatorTierConfig, SavedSearch, DeliverableWeightConfig, DeliverableTitleMapping entities + EF migrations | AI | 0.3 | 0.06 | 0.36 | 0.072
1.1 | 1.1b | Creator API Endpoints | All /api/v1/creators/* endpoints: CRUD, search, filters, import, rate cards, travel costs, brand conflicts, tier config, weights, mappings, saved searches, data completion | AI | 0.3 | 0.06 | 0.36 | 0.072
1.1 | 1.1c | Social Data Integration | Social Blade wiring to CreatorSocialMetrics, Phyllo public data client, Apify fallback, nightly batch job, on-demand refresh | Dev X | 1.2 | 0.24 | 1.44 | 0.288
1.1 | 1.1d | Creator Roster | Roster list view with filters + free text search, saved search presets, creator detail view (profile, social metrics, social links), Data completion tracker (21 fields, fill rates, color-coded), Media kit upload + storage | Dev X | 1 | 0.2 | 1.2 | 0.24
1.1 | 1.1e | Rate Card | Rate card tab in creator detail (CRUD, base/min/max, AED/USD toggle), bulk rate review/approval screen, deliverable weight config page, title mapping page | Dev X | 0.8 | 0.16 | 0.96 | 0.192
1.1 | 1.1f | Rate Calculation Engine | Historical rate calculation from PM ProjectLine data, deliverable title mapping (auto + manual), weight matrix decomposition, currency normalization, scheduled recalculation | Ghassan/Dev X | 1 | 0.2 | 1.2 | 0.24
1.1 | 1.1g | Bulk Import Creator | CSV/Excel import with template download, validation, preview, error reporting, auto social fetch. | Dev X | 0.5 | 0.1 | 0.6 | 0.12
1.1 | 1.1h | Travel Costs | Travel costs CRUD for non-UAE creators | Dev X | 0.5 | 0.1 | 0.6 | 0.12
1.2 |  | Proposal Feature |  |  | 4.5 | 0.9 | 5.4 | 1.08
1.2 | 1.2a | Proposal Entity Layer | Proposal, ProposalLine, ProposalApproval, ProposalTemplate, ApprovalMatrix entities + EF migrations | AI | 0.3 | 0.06 | 0.36 | 0.072
1.2 | 1.2b | Proposal API Endpoints | All /api/v1/proposals/* endpoints: CRUD, duplicate, approval actions, won/lost, create-project, document versions. Templates, approval matrix endpoints | AI | 0.4 | 0.08 | 0.48 | 0.096
1.2 | 1.2c | Proposal Creation | Campaign brief input form (client lookup, BU, budget, platforms, language), manual creator selection from roster, deliverable entry per line, pricing (Amount/Cost/Percentage/Travel), (AI placeholder for phase 2) | Dev X | 1.5 | 0.3 | 1.8 | 0.36
1.2 | 1.2d | Document Generation | PDF/Word proposal generation using BU templates, multi-language (EN/AR/EN+AR sequential), Azure Blob versioned storage, document preview/download | Dev X | 1 | 0.2 | 1.2 | 0.24
1.2 | 1.2e | Approval Workflow | Configurable approval matrix (per BU + deal size), multi-step sequential approval, Approve/Reject/RequestChanges with comments, email + in-app notifications | Dev X | 0.5 | 0.1 | 0.6 | 0.12
1.2 | 1.2f | Proposal Lifecycle | Status transitions (Draft to Won/Lost), won deal tracking (ActualRevenue, WonDate), lost reason, Create Project from Proposal, duplicate, reference numbers | Dev X | 0.8 | 0.16 | 0.96 | 0.192
1.3 |  | Dashboard & Reporting |  |  | 3.2 | 0.64 | 3.84 | 0.768
1.3 | 1.3a | Pipeline Dashboard | Proposal (count + value by status), revenue by client chart, revenue by year chart, role-based views (TM/BU Head/Executive), financial restrictions | Dev X | 1.5 | 0.3 | 1.8 | 0.36
1.3 | 1.3b | Deals View | Won proposals grouped by client (accordion), KPI cards, revenue by year, inline editing (notes, actual revenue), Create Project button, link to proposal | Dev X | 1.2 | 0.24 | 1.44 | 0.288
1.3 | 1.3d | Excel Export | Dashboard data export to Excel across all views | Dev X | 0.5 | 0.1 | 0.6 | 0.12
1.4 |  | Admin |  |  | 3 | 0.6 | 3.6 | 0.72
1.4 | 1.4a | Admin | Tier config, weight config, title mapping, template editor, approval matrix config, API key management, data completion overview, AI prompt placeholder (read-only) | Dev X | 3 | 0.6 | 3.6 | 0.72
1.5 |  | Testing |  |  | 4 | 0.8 | 4.8 | 0.96
1.5 | 1.5a | Test Phase 1 | QA test phase 1 | QA X | 4 | 0.8 | 4.8 | 0.96
|  | Phase 1 Subtotal |  |  | 20.3 | 4.06 | 24.36 | 4.872 | 3410.4
Phase 2 — AI Integration
2 | 2.1 | Claude API Service Layer | Claude Sonnet + Haiku API client, authentication, error handling, retry logic, token usage tracking | Ghassan/Dev X | 1 | 0.2 | 1.2 | 0.24 |  | Will start on it while working on after 2 weeks from phase 1
2 | 2.2 | AI Brief Expansion | Replace placeholder: rough brief to structured brief (audience, categories, tiers, tone) via Sonnet | Dev X | 2 | 0.4 | 2.4 | 0.48
2 | 2.3 | AI Creator Ranking | Replace placeholder: brief + roster to scored shortlist with justifications via Sonnet | Dev X | 3 | 0.6 | 3.6 | 0.72
2 | 2.4 | AI Deliverable Recommendation | AI suggests deliverables per creator based on campaign objectives | Dev X | 1 | 0.2 | 1.2 | 0.24
2 | 2.5 | AI Narrative Generation | Replace placeholder: generates professional proposal narrative (EN/AR/EN+AR) via Sonnet | Dev X | 1 | 0.2 | 1.2 | 0.24
2 | 2.6 | Maker/Checker Validation | Haiku audits all Sonnet outputs against raw DB data, >10% mismatch = human review flag | Ghassan/Dev X | 3 | 0.6 | 3.6 | 0.72
2 | 2.7 | Campaign Memory Builder | Service aggregates won proposals as context for Claude recommendations | Dev X | 1 | 0.2 | 1.2 | 0.24
2 | 2.8 | Prompt Version Control | AiPromptVersion entity fully active, admin CRUD, version promotion, 5 predefined prompts seeded | Ghassan/Dev X | 2 | 0.4 | 2.4 | 0.48
2 | 2.9 | Pattern Analysis | Repeat creators detection, client tier preferences, highest value creators, category trends, win rates by BU/tier/category | Ghassan/Dev X | 2 | 0.4 | 2.4 | 0.48
2 | 2.1 | Test Phase 2 | QA testing Phase 2 | QA X | 5 | 1 | 6 | 1.2
|  | Phase 2 Subtotal |  |  | 21 | 4.2 | 25.2 | 5.04 | 3528
Phase 3 — Enhancements
3 | 3.1 | HypeAuditor Integration | Audience quality API, fake follower detection, credibility scoring, badge display | Dev X | 3 | 0.6 | 3.6 | 0.72
3 | 3.2 | Advanced Deliverable Types | Expand from 4 to 8 types (SocialPost, StoryPackage, BrandAmbassador, ExclusivityFee), update rate cards, weights, mappings | Dev X | 1 | 0.2 | 1.2 | 0.24
3 | 3.3 | Phyllo Full Auth | Creator-authenticated OAuth flow, audience demographics collection, webhook real-time refresh | Dev X | 2 | 0.4 | 2.4 | 0.48
3 | 3.4 | Redis Caching | Brief embeddings cache (7 days), creator profiles cache (24 hours), cache-before-AI strategy | Ghassan/Dev X | 2 | 0.4 | 2.4 | 0.48
3 | 3.5 | Cosine Similarity Scoring | Vector embeddings for briefs and creator profiles, semantic matching for recommendations | Ghassan/Dev X | 2 | 0.4 | 2.4 | 0.48
3 | 3.6 | Token Budget Enforcement | Alert at 70% usage, hard stop at 100%, cost reporting dashboard, per-BU tracking | Ghassan | 3 | 0.6 | 3.6 | 0.72
3 | 3.7 | Prompt Eval Sets | Evaluation dataset creation, automated prompt testing, regression detection | Ghassan/Dev X | 2 | 0.4 | 2.4 | 0.48
3 | 3.8 | Advanced Approval Workflows | Multi-path approvals, delegation, escalation, conditional routing | Ghassan/Dev X | 3 | 0.6 | 3.6 | 0.72
3 | 3.9 | Arabic RTL UI | Full Arabic language support in frontend, RTL layout, translated labels and database | Dev X | 4 | 0.8 | 4.8 | 0.96
3 | 3.10 | Auto-Discovery | Weekly Apify scraping for new creators matching target categories, review queue | Dev X | 4 | 0.8 | 4.8 | 0.96
3 | 3.11 | Predictive Revenue Forecasting | AI-driven pipeline forecasting from historical data, confidence intervals, dashboard widget | Ghassan/Dev X | 4 | 0.8 | 4.8 | 0.96
3 | 3.12 | Client Self-Serve Portal | Separate API layer, SAS token document sharing, client authentication, client dashboard | UI/Ghassan/Dev X | 5 | 1 | 6 | 1.2
3 | 3.13 | AI Integration Testing | End-to-end testing of all AI flows, Maker/Checker accuracy validation, prompt tuning | Dev X | 3 | 0.6 | 3.6 | 0.72
|  | Phase 3 Subtotal |  |  | 38 | 7.6 | 45.6 | 9.12 | 6384
|  | PROJECT TOTAL |  |  | 91 | 18.2 | 109.2 | 21.84 | 15288

## Open Questions
# | Question | Owner | Status | Priority | Target Phase | Notes
1 | Social Blade API tier and rate limits — confirm plan details | Ghassan | Open | High | Phase 0
2 | Specific Apify actors per platform + budget constraints | Ghassan | Open | Medium | Phase 1
3 | Full list of 10 business unit names and codes | Comms Visioneers | Open | High | Phase 0
4 | Approval chain definitions per BU — who approves, deal size thresholds | Comms Visioneers | Open | High | Phase 1
5 | BU template branding assets delivery timeline (logos, colors, fonts) | Comms Visioneers | Open | Medium | Phase 1
6 | Creator data privacy / consent — legal review needed before client portal | Comms Visioneers | Open | Low | Phase 3
7 | Deliverable types: 4 simple (Phase 1) or expand to 8? Client to confirm | Comms Visioneers | Open | Medium | Phase 1/3
8 | Phyllo pricing tier + per-creator costs | Ghassan | Open | High | Phase 0
9 | Confirm Item master has entries for deliverable types or seed needed | Ghassan | Open | High | Phase 0
10 | Claude API budget cap — monthly limit for AI features | Ghassan | Open | High | Phase 2
11 | List of Role allowed in VCI? | Comms Visioneers | Open | High | Phase 0
12 | PM ProjectLine cost field confirmation — which field stores per-creator cost? | Comms Visioneers | Open | High | Phase 1 | Confirmed: ProjectLine.Cost
13 | What is the different between Deal and Proposal ? | Comms Visioneers | Open | High | Phase 0
14 | Is Each BU have different workflow for approval ? | Comms Visioneers | Open | High | Phase 1
15 | Should add Admin UI to be part of Portal ? | Comms Visioneers | Open | High | Phase 1
16 | Do you need to support Brand Conflict so a creator can't be selected if already used with a competitor client? | Comms Visioneers | Open | High | Phase 1
17 | We do have project VSupplier where a supplier/creator can access their data and see all projects linked with them and see all payments and pending payments for each project. Will this be updated too with Creator DB? | Comms Visioneers | Open | Medium | Phase 1
18 | For a creator, we can have an Agent that manages him/her. Do we care about the agent? Setup already used in VPortal? | Comms Visioneers | Open | Medium | Phase 1
19 | For the Client Portal, what are the requirements — is it only to create a quotation, and then VCI Portal will verify? | Comms Visioneers | Open | High | Phase 1
20 | Why do we need to have a separate instance with a different URL? | Comms Visioneers | Open | Medium | Phase 1

## Assumptions
# | Assumption | Impact if Wrong | Phase | Status
1 | Existing creator data in VPortal Supplier table is accurate and serves as initial roster | Need data cleanup before launch; delay Phase 1 | Phase 1 | Assumed
2 | Social Blade API key is available and active with sufficient rate limits | Social metrics unavailable until key provisioned | Phase 1 | Confirmed
3 | VPortal Identity module will be used to authenticate VCI | Need custom auth implementation; delay Phase 0 | Phase 0 | To Verify
4 | Phyllo account will be set up before Phase 1 development | Social data limited to Social Blade only; reduced quality | Phase 1 | To Verify
5 | Claude API subscription provisioned before Phase 2 | AI features cannot be tested or deployed | Phase 2 | To Verify
6 | Visioneers will provide BU branding assets (logos, colors, fonts) before Phase 1 proposal module | Default template only; BU-specific templates delayed | Phase 1 | To Verify
7 | Visioneers will define approval chain configurations before Phase 1 | Approval workflow ships with placeholder/default config | Phase 1 | To Verify
8 | Historical PM project data contains sufficient creator cost and deliverable info for rate calculation | Rate calculation produces inaccurate or no results; manual only | Phase 1 | To Verify
9 | Internal teams work primarily in English; Arabic needed for proposals only | Arabic RTL UI needed earlier than Phase 3 | Phase 1 | Assumed
10 | Claude Code (AI-assisted development) significantly accelerates development velocity | Timeline estimates may be optimistic | All | Assumed
11 | VPortal Admin/Manager/Viewer role structure maps to VCI RBAC needs | Need custom role definitions; additional auth work | Phase 0 | To Verify
12 | Azure Blob Storage is already provisioned and accessible from VPortal API | Need new storage account setup; delay Phase 0 | Phase 0 | Confirmed
13 | All IP (code, data, AI prompts) belongs to Visioneers from day one | Contract/legal review needed | All | Assumed
| Will use same database and Application service in azure for Vportal so there is no additional cost for hosting | Hosting in Azure | All | Confirmed

## Variables
Flat Cost Per Hour | 20
Hours per day | 7
Hour per week | 35